Set-Up Phase

- Send campaign planning doc to client and set up kickoff meeting (pre-kickoff)**

- Send out Calendar Invite with Online Meeting Details (pre-kickoff)**

- Hold kickoff meeting

- Join LinkedIn groups (start 1 day after kickoff. To be completed within 5 days of kickoff meeting)

- Send kickoff meeting follow-up email (1 day after kickoff)**

- Update your notes with scope of work, payment info, client data, prospect profile (1 day after kickoff)

- Update Task Manager (1 day after kickoff)

- Set up Feedly feeds (2 days after kickoff)

- Profile optimization (3 days after kickoff)**

- Practice database build (7 days after kickoff)

- Email client group name ideas (8 days after kickoff)**

- Export original connections (9 days after kickoff)

- Send client email alerting to database build (9 days after kickoff)**

- Begin database build (10 days after kickoff)

- Email client to check progress of database build (11 days after kickoff)**

- Build LinkedIn group (14 days after kickoff)**

- Gather first batch of content (16 days after kickoff)**

- Begin posting content in LinkedIn group (19 days after kickoff)

- Draft script for the messaging campaign (20 days after kickoff)**

- Export and de-dup connections and send to client to mark DNM (23 days after kickoff)**

Ongoing Month 1

- Launch LinkedIn group (30 days after kickoff)**

- Prep for messaging campaign (31 days after kickoff)

- Send out messaging campaign (32 days after kickoff meeting)**

- Gather content** (Gather enough for 2 weeks)

- Gather content

- Send out group invites

- Weekly check-in with client

- Weekly check-in with client

- Weekly check-in with client

- Weekly check-in with client

- Create monthly status report (only needed if the client is already getting leads)**

- Draft group invite scripts (if needed)

- Update Task Manager with future ongoing work (scheduled out 2 months in advanced)

- First batch of prospects to receive a phone call**

Ongoing Month 2

- Prep for Messaging Campaign

- Send out messaging campaign

- Draft scripts for messaging campaign

- Send out group invites

- Gather content

- Gather content

- Weekly check-in with client

- Weekly check-in with client

- Weekly check-in with client

- Weekly check-in with client

- Create monthly status report (only if client is getting leads)

- Draft group announcement and send to client for approval

- Post group announcement in LinkedIn group

- Update Task Manager with future ongoing work (scheduled out two months out in advanced)